## tasks-milestones-publications
Tasks
T1 SLAM Framework
T1.1 Literature and commercial SLAM frameworks
T1.2 Feature extraction algorithms
T1.3 Data association algorithms
T1.4 Sensor data matching algorithms
T1.5 Feature versus grid-based localization
T1.6 Base SLAM framework for RicoSLAM
T2 Robot Calibration
T2.1 Geometric feature extraction and matching
T2.2 Automatic calibration algorithm
T3 Dynamics Modeling
T3.1 Environment dynamics as a continuous value
T3.2 Dynamics clustering algorithm
T3.3 Data association considering dynamics
T3.4 Map update accounting dynamics
T3.5 Localization accounting dynamics
T4 Test and Validation
T4.1 Integration and validation
T4.2 Data acquisition
T5 PhD Thesis
T5.1 Writing the thesis
T5.2 Scientific dissemination
Milestones
M1 Base SLAM framework for RicoSLAM
M2 Automatic sensor calibration algorithm
M3.1 Dynamics Modeling Estimator
M3.2 RicoSLAM
Publications
P1 Bechmarking of existent SLAM solutions (Article)
P2 Automatic sensor calibration algorithm (Conference Paper)
P3.1 Environment dynamics modeling (Article)
P3.2 Map update accounting the environment dynamics (Conference Paper)
P3.4 RicoSLAM: Long-Term Localization and Mapping in Dynamic Environments (Article)
P4 Long-term SLAM dataset in a changing environment (Article)
#papers | 2
#articles | 4

## timeline
| 2023 (1st year) | [11 empty] | 2024 (2nd year) | [11 empty] | 2025 (3rd year)
Tasks Description | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12
T1 SLAM Framework | bar: 2023 (1st year) 1 to 2024 (2nd year) 6
T1.1 Literature and commercial SLAM frameworks | 2023 (1st year) 1: T1.1
T1.2 Feature extraction algorithms | 2023 (1st year) 4: T1.2
T1.3 Data association algorithms | 2023 (1st year) 5: T1.3
T1.4 Sensor data matching algorithms | 2023 (1st year) 4: T1.4
T1.5 Feature versus grid-based localization | 2023 (1st year) 7: T1.5
T1.6 Base SLAM framework for RicoSLAM | 2023 (1st year) 9: T1.6
T2 Robot Calibration | bar: 2023 (1st year) 7 to 2023 (1st year) 12
T2.1 Geometric feature extraction and matching | 2023 (1st year) 7: T2.1
T2.2 Automatic calibration algorithm | 2023 (1st year) 9: T2.2
T3 Dynamics Modeling | bar: 2024 (2nd year) 1 to 2025 (3rd year) 9
T3.1 Environment dynamics as a continuous value | 2024 (2nd year) 1: T3.1
T3.2 Dynamics clustering algorithm | 2024 (2nd year) 5: T3.2
T3.3 Data association considering dynamics | 2024 (2nd year) 7: T3.3
T3.4 Map update accounting dynamics | 2024 (2nd year) 5: T3.4
T3.5 Localization accounting dynamics | 2025 (3rd year) 1: T3.5
T4 Test and Validation | bar: 2023 (1st year) 1 to 2025 (3rd year) 9
T4.1 Integration and validation | 2024 (2nd year) 1: T4.1
T4.2 Data acquisition | 2023 (1st year) 1: T4.2
T5 PhD Thesis
T5.1 Writing the thesis
T5.2 Scientific dissemination
Milestones Description
M1 Automatic sensor calibration algorithm | bar: 2023 (1st year) 12
M2 Base SLAM framework for RicoSLAM | bar: 2024 (2nd year) 6
M3.1 Dynamics Modeling Estimator | bar: 2024 (2nd year) 10
M3.2 RicoSLAM | bar: 2025 (3rd year) 9
Publications Description
P1 Benchmarking of existent SLAM solutions | bar: 2023 (1st year) 10
P2 Automatic sensor calibration algorithm | bar: 2024 (2nd year) 1
P3.1 Environment dynamics modeling | 2024 (2nd year) 7: P3.1
P3.2 Map update accounting the environment dynamics | 2025 (3rd year) 7: P3.2
P3.4 RicoSLAM | 2025 (3rd year) 10: P3.3
P4 Long-term SLAM dataset in a changing environment | bar: 2025 (3rd year) 10
| 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12
| 2023 (1st year) | [11 empty] | 2024 (2nd year) | [11 empty] | 2025 (3rd year)